## Sheet1
S NO | Defect Description | Current result | Expected result | Steps to reproduce | Reported By | Report Date | Defect/Enhancement | Fixed By | Status | Fixed Date
1 | Signup | email already exists |  |  | KK | 15-02-2020 | Defect | Anurag | Fixed | 15-02-2020
2 | Signup | no email verification |  |  | KK | 15-02-2020 | Defect | Anurag | Fixed | 15-02-2020
3 | Sign in | not able to sign in |  |  | KK | 15-02-2020 | Defect | Anurag | Fixed | 15-02-2020
4 | Wrong company name | Benchkart Service Pvt Ltd | Benchkart Services Pvt Ltd | site wide in footer | KK | 15-02-2020 | Defect | Anurag | Fixed | 15-02-2020
5 | wrong logo | older logo | newer logo |  | KK | 15-02-2020 | Defect | Anurag | Fixed | 15-02-2020
6 | band colour | different from landing page | same as landing page |  | KK | 15-02-2020 | Defect
7 | Wrong Grammar | email id already exist! Please log in | Email id already exists! Please sign in |  | KK | 15-02-2020 | Defect | Anurag | Fixed | 15-02-2020
8 | Error 404 | 404 on clicking logo | should direct to homepage | page 1 click on logo | KK | 15-02-2020 | Defect | Anurag | Fixed | 16-02-2020
9 | English | http://coachx.in/Customer/Post_Project.aspx?id=72 | Let's start |  | KK | 15-02-2020 | Defect |  |  |  | Discuss
10 | no phone no asked for | http://coachx.in/Customer/Post_Project.aspx?id=72 | ask for phone no |  | KK | 15-02-2020 | Defect
11 | English | http://coachx.in/Customer/Post_Project.aspx?id=72 | Basic Information |  | KK | 15-02-2020 | Defect | Anurag | Fixed | 16-02-2020
12 | No Space for Project Description | http://coachx.in/Customer/Post_Project.aspx?id=72 | Need to be able to see 5-6 lines + |  | KK | 15-02-2020 | Defect | krishan | Fixed | 2020-02-17
13 | Format not good | http://coachx.in/Customer/Contactus.aspx | more spacebetween lines + alignment to improve |  | KK | 15-02-2020 | Enhance
14 | English |  | Thank You for posting your requirement! ¦ Yes, I'm OK to be contacted over phone ¦ No, I prefer to be contacted over email only ¦ Preferred time to call
15 | old dates showing up | http://coachx.in/Customer/Contactus.aspx | Calendar cache needs to be clean |  | KK | 15-02-2020 | Defect
16 | English | http://coachx.in/Customer/SetPassword.aspx | Confirmation password does not match. Please retry | enter wrong password | KK | 15-02-2020 | Defect | krishan | Fixed | 2020-02-17
17 | website message | email id wrong | should be right | 9b@gmail.com | KK | 15-02-2020 | Defect | krishan | Fixed | 2020-02-17
18 | Format not good | http://coachx.in/Customer/Post_Talent.aspx | clean ¦ remove wordings on top ¦Change type of Flexi talent to Type of Talent¦ Add content for Part Time & Full Time as hints ¦ Part Time : Remote working only regardless of length of engagement ¦ Full Time : On-site or Remote; better availability of remote talent |  | KK | 15-02-2020 | enhance
19 | Format not good | please see basic details page | Can category & Sub-Category go side by side? Because we need space for Project Description so that I can see atleast 5-6 lines |  | KK | 15-02-2020 | enhance | krishan | Fixed | 2020-02-18
20 | no hint on skills | skills can be written without hints | hint should be same as in partner page |  | KK | 15-02-2020 | Defect | krishan | Fixed | 2020-02-18
21 | spelling | Loaction | Location |  | KK | 15-02-2020 | Defect | krishan | Fixed | 2020-02-18
22 | No State & City API | only text box | need API |  | KK | 15-02-2020 | Enhance | krishan | Fixed | 2020-02-18
23 | formatting is an issue everywhere; the word flexi or flexi talent has to be replaced with Talent everywhere |  |  |  | KK | 15-02-2020 | Defect | krishan | FIxed | 2020-02-18
24 | Planning to start options | immediately, within 30 days, >30 days | Planning to start (NO "in") ¦ options : immediate, within 30 days, > 30 days |  | KK | 15-02-2020 | Defect | krishan | Fixed | 2020-02-18