## Sheet1
Project Value (incl. Taxes) |  | 400000
Project Duration (in Weeks) |  | 17
Project Start Date |  | 2020-02-01
Milestone | Description | % of Project Value | Amount | Days | Start Date | End Date | Customer to Pay on | Partner to Receive on | Invoice Date | Approval Date | Customer Options
1 | Fortnight 1 | 12% | 48000 | 15 | 2020-02-01 | 2020-02-16 | 2020-02-01 | 2020-02-16 | 2020-02-01 | 2020-02-16 | Approve, Message, Dispute
2 | Getting abc ready | 20% | 80000 | 7 | 2020-02-16 | 2020-02-23 | 2020-02-16 | 2020-02-23 | 2020-02-16 | 2020-02-23 | Approve, Message, Dispute
3 | getting def ready | 30% | 120000 | 21 | 2020-02-23 | 2020-03-15 | 2020-02-23 | 2020-03-15 | 2020-02-23 | 2020-03-15 | Approve, Message, Dispute
4 | getting ghi ready | 30% | 120000 | 70 | 2020-03-15 | 2020-05-24 | 2020-03-15 | 2020-05-24 | 2020-03-15 | 2020-05-24 | Approve, Message, Dispute
5 | testing & go live | 8% | 32000 | 10 | 2020-05-24 | 2020-06-03 | 2020-05-24 | 2020-06-03 | 2020-05-24 | 2020-06-03 | Approve, Message, Dispute
6 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | Approve, Message, Dispute
7 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | Approve, Message, Dispute
8 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | Approve, Message, Dispute
9 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | Approve, Message, Dispute
10 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | Approve, Message, Dispute
Note
In most cases, Invoice Date to be same as milestone start date
In some cases (e.g. BPO) Partner may decide to give leeway to Customer & raise invoice later - such that customer's money is blocked for lower no of days
Formulas:
Start Date = [End Date, row above]
End Date = [Start Date]+[Days]
Customer to Pay on = [Invoice Date]
Partner to Receive on = [End Date]
Invoice Date = [Start Date]
Approval Date = [End Date]

## Milestone in contract
Project Value (incl. Taxes) |  | 500000
Project Duration (in Weeks) |  | 20
Project Start Date |  | 2020-02-01
Project End Date |  | 2020-05-31
Milestone | Description | % of Project Value | Amount | Weeks | Start Date | End Date
1 | Fortnight 1 | 10% | 50000 | 2 | 2020-02-01 | 2020-02-14 | Fixed on benchkart logic
2 | Getting abc ready | 20% | 100000 | 3 |  | 2020-03-05
3 | getting def ready | 30% | 150000 | 5 |  | 1930-04-12
4 | getting ghi ready | 30% | 150000 | 5 |  | 2020-05-18
5 | testing & go live | 8% | 40000 | 2 |  | 2020-05-31
6 |  |  | 0 |  |  |  | Total %, amount be 100% of top mentioned values
7 |  |  | 0
8 |  |  | 0
9 |  |  | 0
10 |  |  | 0

## Milesonte in Dashboard
Milestone in
BK input
| Project Value (incl. Taxes) |  | 400000 | [7 empty] | Partner Input
| Project Duration (in Weeks) |  | 17 | [7 empty] | Client Input
| Project Start Date |  | 2020-02-01 | [6 empty] | Drop Downs
| Project End Date |  | 2020-05-31
| Milestone | Description | % of Project Value | Amount | Weeks | Start Date | Due Date | Milestones Approval Status | Funds showing in BK Nodal account | Developer Status | Customer Status | Customer Remarks
| 1 | Fortnight 1 | 12% | 48000 | 2 | 2020-02-01 | 2020-04-14 | Approved | 48000 | Completed | Approved
| 2 | Getting abc ready | 20% | 80000 | 3 |  |  | New | 80000 | In Progress | Escalate
| 3 | getting def ready | 30% | 120000 | 21 |  |  | Not Approved |  | Not Started
| 4 | getting ghi ready | 30% | 15000 | 70 |  |  |  |  | On Hold
| 5 | testing & go live | 8% | 32000 | 10
| 6 |  |  | 0
| 7 |  |  | 0
| 8 |  |  | 0
| 9 |  |  | 0
| 10 |  |  | 0

## Sheet2
We have to create a logic for <12 weeks of project with all possibilities
ORDER ID |  | invoice\ | paid | release | client | BK | supplier
| dkebndljene | 80000 | 80000 | 80000 | ok | ok/not
| edfkjedne'l | 10000 | 8000 |  | not ok
| ekebhfdbjn/ | 50000 | 50000 |  | ok

## Final-Milestone
Project Value (incl. Taxes) |  |  |  | 500000
Project Duration (in Weeks) |  |  |  | 20
Project Start Date |  |  |  | 2020-02-01
Project End Date |  |  |  | 2020-05-31
Milestone | Number | Title | Description | % of Project Value | Amount | Weeks/Days | Start Date | End Date
1 | M1 |  | Fortnight 1 | 10% | 0 | 2 | 2020-02-01 | 2020-02-14
2 | M2 |  | Getting abc ready | 20% | 0 | 3 |  | 2020-03-05
3 | M3 |  | getting def ready | 30% | 0 | 5 |  | 1930-04-12
4 | M4 |  | getting ghi ready | 30% | 0 | 5 |  | 2020-05-18
5 | M5 |  | testing & go live | 8% | 0 | 2 |  | 2020-05-31
6 |  |  |  |  | 0
Upload