## MVP
Area | Action Item | MVP | Ownership | Dependency | Remarks | KK | AS | AR
Platform | Benchkart AI Algorithm | MH | KK | AR | 1st come 1st serve, Top 8-10 allowed to bid, top 3-4 to be shown to customer | Feb 4th
Platform | Signed off workflow by all 3 | MH | AR | AS, KK |  | 15th Feb
Platform | Partner Persona | MH | AR |  | Seek Free Trials & Consultations, Willing to share bench within benchkart partner network |  |  | 29th Jan
Platform | Consultant Persona | MH | AR |  |  |  |  | 29th Jan
Platform | Payment Integration | MH | AR | AS |  |  |  | AS+3
Platform | Coding - Contract | MH | AR | KK |  | 28th Jan |  | KK+5
Platform | Coding - Delivery & Review | MH | AR | KK |  | 28th Jan |  | KK+5
Platform | Customer Persona | MH | AR |  |  |  |  | 31st Jan
Platform | Admin/Management Persona | MH | AR |  |  |  |  | 30th Jan
Platform | Hosting environment | MH | AR |  |  |  |  | 7th Feb
Platform | Collaboration+ | GTH | AR | KK |  | Jan 31st
Platform | International Workloads/ | GTH | AR | AS, KK |  | Mar 21st
Platform | Finalize UX/UI | MH | AR | KK |  | AR+10 |  | 7th Feb
Platform | Static Content | MH | AR | AS, KK |  |  |  | AS,KK+2
Platform | Popular Services | MH | AR | KK |  | Jan 29th |  | KK+1
Platform | Internal Testing | MH | AR |  | Module Wise Dates - AR to send |  |  | 7th Feb
Platform | QA Testing | MH | KK | AR |  | AR+10
Platform | Communication Flow & Templates | MH | KK | AR |  | AR+3
Legal | Customer Agreement | MH | AS
Legal | Partner Agreement | MH | AS
Legal | Contracting Agreement | MH | AS
Legal | Dispute Resolution Process | MH | AS
Legal | FAQs | MH | KK |  |  | 30th Jan
Legal | Partner - With limited visibility - agreement | MH | AS
Legal | Privacy Policy | MH | AS
Legal | IP Policy | MH | AS
Legal | NDA Policy | MH | AS
Finance | Workflow & Invoicing Process - Domestic | MH | AS |  | Customer transaction - end to end/ all scenarios
Finance | Workflow & Invoicing Process - International | GTH | AS
Finance | Defined Commission Process | MH | AS
Finance | Accounting & Recon - BK Finance/ Management View | MH | AS
Finance | Payment Gateway Provider Contract, Nodal Account | MH | AS | KK |  | As per AS
Partner | Margin Structure | MH | KK | AS |  | 27th Jan
Partner | Partner Assessment Framework | MH | KK | AS |  | Feb-1st
Partner | Availability/ Rates for Roles & Manpower - To be taken | GTH | KK | AR |  | Feb-1st
Partner | Partner Profile, Target list | MH | AS | KK |  | Feb-1st
Partner | Partner Collaterals | MH | AS | KK |  | Feb - 8th
Partner | Partner onboarding - Milestones & Targets | MH | AS | AR
Partner | Onboarding - Digital Marketing, Telesales; On-field sales strategy & agency finalization | MH | AS | KK |  | Feb -8th
Partner | Partner Management Process | MH | KK | AS |  | Feb -5th
Business | Customer Acquisition Strategy | GTH | KK |  |  | Feb 15th
Business | Investor Story - Business Plan Pitch | GTH | KK |  |  | Mar 21st
Business | Foreign Entity | GTH | KK |  |  | Mar 21st
Business | Workflow for Contract | MH | KK | AS, AR |  | 28th Jan
Business | Workflow for Delivery & Review | MH | KK | AS, AR |  | 28th Jan

## Masterlist
Area | Action Item | MVP | Dependancy | Remarks
Business Plan | Meet 3-4 Partner each across categories | c
Business Plan | Partner Visit & Analysis Assimilation, Revision in Plan
Business Plan | Categories & Sub-Categories Finalization | c
Business Plan | Partner Strategy, Target List & Onboarding Format finalization
Business Plan | Project Templates, Popular Workloads finalization
Business Plan | Defining Role for Account Manager & Revenue Model
Legal/Compliance | Margin Structure - Supplier, Any other Revenue Lines | c
Legal/Compliance | Taxation, Invoicing, Compliance | y
Legal/Compliance | Supplier Agreement, Customer Agreement | y
Legal/Compliance | GST Registration & Audit Mechanism Finalization
Legal/Compliance | Nodal Account, Payment Gateway & Current Account decision making | y
Platform | Wireframe finalization | c
Platform | Basic Coding completion
Platform | Payment Gateway integration
Platform | Invoicing, Money flow, CN/DN, Taxation etc integration, what solutions | y
Platform | supplier, customer, project manager & management dashboard views | c
Platform | Other content (pictures, videos, about us, etc) integration
Platform | UX/UI & Customer/Supplier journey finalization
Platform | Web hosting decisions & cost implication analysis
Platform | Testing - customer, partner, payment, external validation
Platform | International clients? | y
Supplier Onboarding | Day/Week wise targets across partner segments, finalization of launch date
Supplier Onboarding | Digital Marketing, Telesales; On-field sales strategy & agency finalization | y
Supplier Onboarding | Budget finalization & initiation of work,
Supplier Onboarding | Helpline & process for onboarding, query resolutions, on-field support
Supplier Onboarding | Partner Outreach for approvals, keeping them warm, updates & relationship
Customer acquisition | Marketing strategy development [TG, funnel, triggers, baits, engagement model] | y
Customer acquisition | Collateral development, Videos, Blogs, PR, | y
Customer acquisition | Segment Wise Customer Acqusition targets, conversion%, funnel finalization
Customer acquisition | Personal Networks - Startegy for Own Network/ Work begin
Customer acquisition | Events calendar & ability to leverage, create awareness
Customer acquisition | Field Sales Agencies, Strategy & Targets | y
Customer acquisition | Launch Customer Acqusiition, incl Budget finalization
PM Readiness | Business Plan & Projections, Load Planning, Cloud & Physical resources estimation
PM Readiness | Key Metrices & Ownership, formal roles/KPIs - accountabilities, team& agencies
PM Readiness | Legal, Audit, IT, DR&Backup - Risk mitigation plans in place
Miscellaneous | Content writing - categories, featured products, etc
Miscellaneous | Photoshoot, Videos, Animation, testimonials etc | y
Miscellaneous | Office movement & associated actions
Miscellaneous | Supplier list, customer list - basic online research & data readiness | y

## 23-27th
Area | Action Item | Time Required | owner | Action
Business Plan | Meet 3-4 Partner each across categories | c | AS | 8 partners
Business Plan | Categories & Sub-Categories Finalization | c | KK
Legal/Compliance | Margin Structure - Supplier, Any other Revenue Lines | c | KK | complete
Legal/Compliance | Taxation, Invoicing, Compliance, Legal | y | AS | taxation & invoicw meeting | Business Deck Readiness (AS/KK)
Legal/Compliance | Supplier Agreement, Customer Agreement | y | AS
Legal/Compliance | Nodal Account, Payment Gateway & Current Account decision making | y | AS | meet payment gateway, self understand nodal/ regulation
Platform | Wireframe finalization | c | AR | complete
Platform | Invoicing, Money flow, CN/DN, Taxation etc integration, what solutions | y | AR | self study
Platform | supplier, customer, project manager & management dashboard views | c | AR | KK/AR discussion
Platform | International clients? | y | AR | self study
Supplier Onboarding | Digital Marketing, Telesales; On-field sales strategy & agency finalization | y | KK | not critical
Customer acquisition | Marketing strategy development [TG, funnel, triggers, baits, engagement model] | y | KK | not critical
Customer acquisition | Collateral development, Videos, Blogs, PR, | y | KK | not critical
Customer acquisition | Field Sales Agencies, Strategy & Targets | y | KK | not critical
Miscellaneous | Photoshoot, Videos, Animation, testimonials etc | y | KK | not critical
Miscellaneous | Supplier list, customer list - basic online research & data readiness | y | KK | not critical

## Margin BPOs
CLASSIFICATION OF CUSTOMERS INTO 3 GROUPS | [11 empty] | Partners | BPO Mapping | Customers
Seat Based VOICE > 6 Months | Start-up | Small | Medium | Large | MNC | Remarks | [5 empty] | 20 | Mass Market | Gr 1 |  |  |  |  | 49
Indian | Gr 1 | Gr 1 | Gr 1 | Gr 2 | Gr 3 | Indian Companies | [5 empty] | 7 | Value | Gr 2 | Gr 3 |  |  |  | 1299
Emerging - Global | Gr 1 | Gr 1 | Gr 2 | Gr 3 | Gr 3 | Other Countries | [5 empty] | 3 | Premium | Gr 2 | Gr 3 |  |  |  | 5999
Developed - Global | Gr 2 | Gr 2 | Gr 3 | Gr 3 | Gr 3 | 10 NA, Europe, ANZ | [5 empty] | 30
Seat Based VOICE < 6 Months | Gr 3
All Other Contracts | Gr 3 if Seat based; else 8%, 6%, 4%, 3% in Yr 1,2,3 of ATV
BPO Project Manager
|  |  |  | Benchkart Commission Per Seat Per Month | [8 empty] | Salary | 20 | lpa
|  |  |  | On Contract | Additional Seats from Same Client |  |  | % Margin |  |  |  |  | Travel | 3 | lpa
Seat Cost | Avg | 1% | Group |  | Yr 1 | Yr 2 | Yr3 | On Contract | Yr 1 | Yr 2 | Yr3 |  | Laptop/Mobile | 0.35 | lpa
50K+ | 55000 | 550 | Gr 1 | 2000 | 1500 | 1125 | 750 | 3.6364 | 2.7273 | 2.0455 | 1.3636 |  | Office | 1 | lpa
40-50K | 45000 | 450 | Gr 1 | 1500 | 1125 | 843.75 | 562.5 | 3.3333 | 2.5 | 1.875 | 1.25 |  | Miscellaneous | 0.65 | lpa
30-40K | 35000 | 350 | Gr 1 | 1000 | 750 | 562.5 | 375 | 2.8571 | 2.1429 | 1.6071 | 1.0714 |  | Total Cost | 25 | lpa
20-30K | 25000 | 250 | Gr 1 | 700 | 525 | 393.75 | 262.5 | 2.8 | 2.1 | 1.575 | 1.05 |  | Total Cost | 35714.2857 | USD
<20K | 18000 | 180 | Gr 1 | 500 | 375 | 281.25 | 187.5 | 2.7778 | 2.0833 | 1.5625 | 1.0417 |  | Margin | 4285.7143 | 12%
Seat Cost | Avg | 1% | [11 empty] | 40000
50K+ | 55000 | 550 | Gr 2 | 2500 | 1875 | 1406.25 | 937.5 | 4.5455 | 3.4091 | 2.5568 | 1.7045
40-50K | 45000 | 450 | Gr 2 | 1875 | 1406.25 | 1054.6875 | 703.125 | 4.1667 | 3.125 | 2.3438 | 1.5625
30-40K | 35000 | 350 | Gr 2 | 1250 | 937.5 | 703.125 | 468.75 | 3.5714 | 2.6786 | 2.0089 | 1.3393 | Project Management Packages |  |  |  | Annual | Monthly | Annual | Monthly
20-30K | 25000 | 250 | Gr 2 | 875 | 656.25 | 492.1875 | 328.125 | 3.5 | 2.625 | 1.9688 | 1.3125 | 1 | Dedicated PM |  |  | 28 | 3 | 40K | 4K
<20K | 18000 | 180 | Gr 2 | 625 | 468.75 | 351.5625 | 234.375 | 3.4722 | 2.6042 | 1.9531 | 1.3021 | 2 | Shared PM - Premium |  |  | 2.8 | 0.3 | 4K | 0.5K
Seat Cost | Avg | 1% | [9 empty] | 3 | Shared PM - Basic |  |  | 1.4 | 0.15 | 2K | 0.25K
50K+ | 55000 | 550 | Gr 3 | 3000 | 2250 | 1687.5 | 1125 | 5.4545 | 4.0909 | 3.0682 | 2.0455 |  |  |  |  | INR Lacs |  | USD
40-50K | 45000 | 450 | Gr 3 | 2250 | 1687.5 | 1265.625 | 843.75 | 5 | 3.75 | 2.8125 | 1.875
30-40K | 35000 | 350 | Gr 3 | 1500 | 1125 | 843.75 | 562.5 | 4.2857 | 3.2143 | 2.4107 | 1.6071
20-30K | 25000 | 250 | Gr 3 | 1050 | 787.5 | 590.625 | 393.75 | 4.2 | 3.15 | 2.3625 | 1.575
<20K | 18000 | 180 | Gr 3 | 750 | 562.5 | 421.875 | 281.25 | 4.1667 | 3.125 | 2.3438 | 1.5625

## Margin Others
All Non BPO | All Companies | [7 empty] | Legal Opinion to be sourced on
Indian | Gr 1 | [7 empty] | when you are accepting work for a client, you are representibg that you are not working with that client already
Emerging - Global | Gr 2 | [8 empty] | except in those cases where client is inviting an existing (non onboarded) agency to participate in process through bk
Developed - Global | Gr 3 | [7 empty] | you will self-declare the revenues earnt from such client post contract quarterly in your dashboard and either
bk will deduct its commission from payables to you from same or different clients
[5 empty] | Additional Revenues from Same Client |  |  |  |  | or you will deposit the commission cheque in bk's bank account under intimation to bk
Project Value (INR) | Avg | 1% | Group | On Contract | Yr 1 | Yr 2 | Yr3 | Avg Margin | any discrepancy will invite a penalty of upto 10 lac, if not corrected within 3 months of notice from bk on same
<1 lac | 20000 | 200 | Gr 1 | 8% | 6% | 4.5% | 3% | 1600 | this includes any attempt to circumvent the initial handshake
1-2.5 Lacs | 150000 | 1500 | Gr 1 | 7% | 5.25% | 3.938% | 2.625% | 10500
2.5-5 Lacs | 350000 | 3500 | Gr 1 | 6% | 4.5% | 3.375% | 2.25% | 21000
5-10 lacs | 700000 | 7000 | Gr 1 | 5% | 3.75% | 2.813% | 1.875% | 35000
10 lacs+ | 1500000 | 15000 | Gr 1 | 4% | 3% | 2.25% | 1.5% | 60000 | Potential Impact on circumvention at outset only!
Project Value (USD) | Avg | 1%
<1K | 25000 | 250 | Gr 2 | 10% | 7.5% | 5.625% | 3.75% | 2500
1-5K | 200000 | 2000 | Gr 2 | 8.75% | 6.562% | 4.922% | 3.281% | 17500
5-10K | 500000 | 5000 | Gr 2 | 7.5% | 5.625% | 4.219% | 2.812% | 37500
10-25K | 1000000 | 10000 | Gr 2 | 6.25% | 4.688% | 3.516% | 2.344% | 62500
25K+ | 2000000 | 20000 | Gr 2 | 5% | 3.75% | 2.813% | 1.875% | 100000
Project Value (USD) | Avg | 1%
<1K | 25000 | 250 | Gr 3 | 12% | 9% | 6.75% | 4.5% | 3000
1-5K | 200000 | 2000 | Gr 3 | 10.5% | 7.875% | 5.906% | 3.938% | 21000
5-10K | 500000 | 5000 | Gr 3 | 9% | 6.75% | 5.062% | 3.375% | 45000
10-25K | 1000000 | 10000 | Gr 3 | 7.5% | 5.625% | 4.219% | 2.813% | 75000
25K+ | 2000000 | 20000 | Gr 3 | 6% | 4.5% | 3.375% | 2.25% | 120000

## Listing Fees
| Platinum | Gold | Regular | Remarks
Fees | 150000 | 50000 | 25000 | Jan-March only Regular plan & Listing fees waived off
per | qtr | qtr | qtr
| 450000 | 150000 | 75000
| Annual | Annual | Annual
Benefit
Bid Position | No. 1 | No. 2 | No. 3
Tagging | Platinum | Gold | None
Joint Account Planning | qtrly | half yrly | None
Insights Sharing | qtrly | half yrly | None
Articles/ Blogs | 2 | 1 | None
Video Interview | 1 | 0 | None
Company Promo 2-3 min | 1 | 0 | None

## Customer Subscription
| Platinum | Gold | Silver | Regular | Remarks
Fees |  |  |  |  | Jan-Jun only Regular plan & subscription fees waived off; Upfront payment of Min Value - balance settled basis projects
of
Per | half year | month | Project
Min | 200000 | 15000 | 5000
Benefit
Recruiter | Y | Y | Y
Project Manager | Y | Y
Account Management | Y
Account Management deliverables
Joint Account Planning | 1
Insights Sharing | ongoing
Joint Review | 2
BK Management Review | 1

## Why Agency
PROs | Agency Vs Freelancers
1 | Better on reliability, manageability, complex tasks & support
2 | More differentiated; Agencies love someone supporting them only
3 | International clients love single point access to Indian agencies for outsourcing
4 | Exclusive categories e.g. BPO, staffing
5 | Possible to leverage clients as suppliers - to share best practices
CONs | Agency Vs Freelancers
1 | Cant impress with nos like 100000+ professionals
2 | Sometimes may be costlier than freelancers
3 | Circumvention is tougher to solve
4 | Biz Model may appear to be going against the flow

## Sheet3
BPO Service Providers
| Denave | Arvato
isource
Doon Consulting